## RCS
REVIEW AND COMMENT SHEET
TEMPLATE REFERENCE: RUA-DEV-TMP-0026
REVIEWED DOCUMENT DATA |  | RCS DATA
Transmittal / Document Ref. |  | RCS Identification: |  | Sign / Date
Transmittal / Document Title |  | Status Code: |  | Sign / Date
Document Type |  | RCS Prepared by: |  | Sign / Date
Discipline(s) Involved |  | Reviewer – RCS Reviewed by: |  | Sign / Date
|  | Reviewer – RCS Approved by: |  | Sign / Date
|  | RUA No Objection by: |  | Sign / Date
Transmittal Received Date |  |  |  | Sign / Date
Disclaimer: Permission to proceed shall not constitute acceptance or approval of design details, calculations, analyses, test methods or materials developed or selected by the Contractor and shall not relieve the Contractor from full compliance with Contractual obligations and RUA requirements.
STATUS CODES (per RUA-DEV-GDN-0001): A = Approved – Proceed ¦ B = Approved with Comments – Proceed ¦ C = Revise & Resubmit – Do Not Proceed ¦ D = Rejected – Do Not Proceed
A – Approved | B – Approved with Comments | C – Revise & Resubmit | D – Rejected

## DATA LIST
DATA LISTS & LOOKUP TABLES
Code | Label | Colour | Workstream | Topic | Discipline | Submission | Revision | Workstream List | CRITICAL
A | Approved |  | MASTERPLANNING | SGS Guidelines Impacts | Architecture | Baseline | V01 | MASTERPLANNING | High
B | Approved with Comments |  | MASTERPLANNING | Main plot standalone approach | Civil | Stage 2A | V02 | MOBILITY | Medium
C | Revise & Resubmit |  | MASTERPLANNING | Main Plot – Redefining Diamond Plot Boundaries | Structural | Stage 2B | V03 | PUBLIC REALM | Low
D | Rejected |  | MASTERPLANNING | Main Plot - Undercroft Diagrids & Unique Parcel Names | Mechanical |  |  | INFRASTRUCTURE
|  |  | MASTERPLANNING | Main Plot – Integration of Security Building 03 & PSS | Electrical
|  |  | MASTERPLANNING | Civic Site – Parking Self Sufficiency of Plots | Plumbing
|  |  | MASTERPLANNING | MP Key Assumptions | Landscape
|  |  | MASTERPLANNING | VA Integration Assumptions - Floor to Floor Tower Heights | Environmental
|  |  | MOBILITY | Ring Road Connector integration strategy | Fire Protection
|  |  | MOBILITY | Temporary & Permanent Bus Stations | Infrastructure
|  |  | MOBILITY | Latest RCMC Metro Network & Al Sulaymaniyah Station | Roads
|  |  | MOBILITY | Jarwal Multimodal Hub | Bus Stations
|  |  | MOBILITY | Paramobility Network | Metro Stations
|  |  | MOBILITY | Parking Assumptions | Wet Utilities
|  |  | PUBLIC REALM | Roads, Slopes revisions & Fire Life Safety | Dry Utilities
|  |  | PUBLIC REALM | Redistribution of Fire Stations & new response time | District Cooling
|  |  | PUBLIC REALM | Umm AlQura Road & Jabal AlKaabah Road Extension | Logistics
|  |  | PUBLIC REALM | Re routing of Jarwal & Al Sulaymaniyah Pedestrian Spines | Crowd
|  |  | PUBLIC REALM | Pedestrian Tunnel 02 Integration strategy | Sustainability
|  |  | PUBLIC REALM | AlHaram Entrance Gate Zone-16 integration | Constructability
|  |  | PUBLIC REALM | Assessment of Latest RCMC Crowd Data | Phasing
|  |  | PUBLIC REALM | Latest Prayer Facility Requirements | Stakeholder
|  |  | PUBLIC REALM | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Topo
|  |  | INFRASTRUCTURE | Existing Utilities integration strategy | GI
|  |  | INFRASTRUCTURE | MOF Assets integration strategy | Mobility
|  |  | INFRASTRUCTURE | Fan Stations Integration strategy | Energy-Power
|  |  | INFRASTRUCTURE | MCA servicing strategy | MP
Energy-Cooling
District Cooling

## MASTERPLANNING
REVIEW AND COMMENT SHEET |  |  | WorkStream: | MASTERPLANNING
| Submission: | Baseline | Revision: | V01 | Doc Ref.: |  | Prepared by: |  |  |  | Date:
COMMENT IDENTIFICATION | [5 empty] | ROUND 1 – CLIENT / RUA |  |  |  | ROUND 1 – DESIGNER RESPONSE |  |  | ROUND 2 – CLIENT / RUA |  |  |  | ROUND 2 – DESIGNER RESPONSE |  |  | ROUND 3 – CLIENT / RUA |  |  |  | ROUND 3 – DESIGNER RESPONSE |  |  | FINAL (CLIENT ONLY)
No. | Submission | Milestone | Topic | Doc / Drawing Ref. | Discipline | R1 – RUA Comment | R1 – Comment By | R1 – Status (CLIENT ONLY) | CRITICAL | R1 – Designer Response | R1 – Response By | R1 – Response Date | R2 – RUA Comment | R2 – Comment By | R2 – Status (CLIENT ONLY) | CRITICAL | R2 – Designer Response | R2 – Response By | R2 – Response Date | R3 – RUA Comment | R3 – Comment By | R3 – Status (CLIENT ONLY) | CRITICAL | R3 – Designer Response | R3 – Response By | R3 – Response Date | Final Status (CLIENT ONLY) | CRITICAL | Remarks / Notes
1 | Baseline | Step I | SGS Guidelines Impacts | Page # 22 Underground Tunnel clashes with Ground Water | Mobility | It is mentioned" Tunnel/ C&C below water table", please advise which Technology is being used for Cut & Cover tunneling under water table? | NNF | B
2 | Baseline | Step I | SGS Guidelines Impacts | Page # 38 Impact of SGS Guidelines - Marwa Metro Station Layout Adjustment | Mobility | Please confirm whether the queuing spaces for Marwa Metro station are still retained at Upper and Lower metro station concourse. | HR | B
3 | Baseline | Step I | SGS Guidelines Impacts | Page #41 Impact of SGS Guideline - Revised Circulation Schemes | Mobility | Please confirm the direct access from Shaeb Amer bus station to AlHaram are still bi-directional and that there will be internal escalators to take the crowd up to upper concourse level where passengers waiting area are located. Please also allow for queuing areas at the lower bus concourse level. | HR | B
4 | Baseline | Step I | SGS Guidelines Impacts | Page #42 Impact of SGS Guideline - Revised Circulation Schemes | Mobility | As per CMP report's Crowd Management section, projected passenger capacity for Shaeb Amer Station is 137,700 pp/hr. This consists of 91,800 pp/hr (within station) ie. 48K m2 and 45,900 pp/hr (external plaza area). If queuing area size is based on LOS D (0.28 - 0.65m2/pax), do we have adequate plaza queuing area of 29,835 m2 at Zamzam plaza? | HR | C
5 | Baseline | Step I | SGS Guidelines Impacts | Page#120 Impact on Utility Demands | Energy-Power | Updated power demand is required to be mentioned as well in the form of phasing demand (power demand for each project phase), considering SGS impact and GFA compensation. | Ahmed Rakha | B
6 | Baseline | Step I | SGS Guidelines Impacts | Page#120 Impact on Utility Demands | Energy-Power | We request the consultant to verify the most updated power and cooling demand for the entire Phase-1, taking into consideration the impact of SGS requirements and evaluate the feasibility of replacing the two proposed compact substations within the Phase 1 boundary with a single conventional substation located adjacent to DCP-1, outside the main plot, within the proposed area for DCP-1. | Ahmed Rakha | B
7 | Baseline | Step I | SGS Guidelines Impacts | MCMP Comments Tracker | Infrastructure | comment no. 12 in the MCMP comments tracker still open, to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
8 | Baseline | Step I | SGS Guidelines Impacts | Page #20–21 – Impact of SGS Guidelines / Ground Investigation Status | MP | Provide a consolidated summary identifying all approved workshop assumptions and directions adopted under the SGS impact assessment to ensure traceability into DMP development. | PgMC | B
9 | Baseline | Step I | SGS Guidelines Impacts | Page #21 – Impact of SGS Guidelines / Ground Investigation Status | MP | Clarify whether additional plot assessments will follow the same SGS methodology adopted for the Main Plot and identify potential downstream impacts on the overall masterplan. | PgMC | B
10 | Baseline | Step I | SGS Guidelines Impacts | Page #18–20 – Ground Water Data & Analysis | MP | Demonstrate how SGS-related constraints have been integrated into the masterplan design principles, including implications on plot configuration and future development flexibility. | PgMC | B
11 | Baseline | Step I | SGS Guidelines Impacts | Page #20 – Ground Water Data & Analysis | MP | Further clarify interfaces between SGS findings and dependent workstreams to ensure no unresolved planning assumptions are transferred into subsequent DMP stages. | PgMC | B
12 | Baseline | Step I | SGS Guidelines Impacts | General / SGS Guidelines Impacts | MP | Update the submission to identify remaining stakeholder dependencies and required decisions prior to design freeze. | PgMC | B
13 | Baseline | Step I | SGS Guidelines Impacts | Page #21 – Ground Investigation Status | MP | Clearly identify assumptions adopted for progression into DMP Stage 1 pending completion of the GI campaign, and distinguish confirmed inputs from temporary assumptions. | PgMC | B
14 | Baseline | Step I | SGS Guidelines Impacts | Page #20 – Ground Water Data & Analysis | MP | Provide a risk register identifying potential masterplan impacts if final GI findings differ from current assumptions, including impacts on development capacity, tower configurations, and infrastructure interfaces. | PgMC | B
15 | Baseline | Step I | SGS Guidelines Impacts | Page #18–21 – SGS Guidelines Impacts | MP | Confirm agreed workshop outcomes and identify any open items requiring RUA direction prior to design freeze. |  | B
16 | Baseline | Step I | Main plot standalone approach | Page#66 &124 Dry and Wet Infrastructure Impact | Energy-Cooling | The mentioned cooling demand for the main plot only (121,862 TR / 106,970 TR) shall be revised as it appears not to be a correct numbers. | Ahmed Rakha | C
17 | Baseline | Step I | Main plot standalone approach | Page#174-185 Relocation of Dry Infrastructure Options | Energy-Power | It is RUA's preference to locate the primary substation adjacent to the DCP to consolidate utilities within a single utility hub, minimize the extent of cabling and utility tunnels between the PSS and DCP, as well as all associated costs. Accordingly, we request the consultant to assess the feasibility of replacing the two proposed compact substations within the Phase-1 boundary with a single conventional substation (after considering the dramatic reduction of energy demand due to SGS impact), this conventional PSS should be attached to DCP-1, outside the main plot, within the highlighted area for DCP-1. | Ahmed Rakha | C
18 | Baseline | Step I | Main plot standalone approach | Page#174-185 Relocation of Dry Infrastructure Options | Energy-Cooling | As the proposed location of DCP-1 is situated within a mountain-cut area, we would like to raise a concern regarding the potential enclosure of the plant by adjacent mountain formations from one or more sides. This condition may adversely impact the cooling tower air circulation and thermal performance, in addition to affecting plant accessibility and the long-term equipment replacement strategy. Accordingly, we request the consultant to study the proposed elevation and overall height of DCP-1 in relation to the surrounding mountain levels, as well as to assess and confirm the adequacy of the proposed access roads for equipment delivery, maintenance, and future replacement activities. | Ahmed Rakha | C
19 | Baseline | Step I | Main plot standalone approach | MCMP Comments tracker | Infrastructure | comments nos. 18, 25, 26, 31, 32 and 33 in the MCMP comments tracker still open, to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
20 | Baseline | Step I | Main plot standalone approach | Page #64–66 – Main Plot Standalone Strategy | MP | Confirm the agreed workshop position regarding the preferred standalone scenario and clearly identify assumptions adopted for progression into DMP. | PgMC | B
21 | Baseline | Step I | Main plot standalone approach | Page #64–66 – Main Plot Standalone Strategy | MP | Further demonstrate the operational feasibility of relocating supporting facilities outside the Main Plot, including dependencies and interface requirements. | PgMC | B
22 | Baseline | Step I | Main plot standalone approach | Page #65 – Preferred Scenario Summary | MP | Clarify the long-term implications of the proposed Main Plot boundary modifications and identify any future land acquisition or adjacent plot dependencies. | PgMC | B
23 | Baseline | Step I | Main plot standalone approach | Page #64 – Impact Analysis | MP | Provide a consolidated assessment of impacts on mobility, crowd management, infrastructure, and phasing arising from the standalone development approach. | PgMC | B
24 | Baseline | Step I | Main plot standalone approach | Page #65 – Preferred Scenario Summary | MP | Confirm outstanding stakeholder decisions and workshop action items required prior to design freeze to avoid downstream masterplan modifications. | PgMC | B
25 | Baseline | Step I | Main Plot – Redefining Diamond Plot Boundaries | Page #93–95 – Main Plot: Re-defining Diamond Plot Boundaries | MP | Clearly define the final plot boundary principles adopted during the workshop and demonstrate alignment with public/private ownership requirements. | PgMC | B
26 | Baseline | Step I | Main Plot – Redefining Diamond Plot Boundaries | Page #93–95 – Main Plot: Re-defining Diamond Plot Boundaries | MP | Provide assessment of impacts resulting from revised plot boundaries on plot efficiency, development capacity, and future design flexibility. | PgMC | B
27 | Baseline | Step I | Main Plot – Redefining Diamond Plot Boundaries | Page #94–95 – Main Plot: Re-defining Diamond Plot Boundaries | MP | Clarify interfaces between revised plot boundaries and adjacent infrastructure/utilities to ensure no downstream conflicts are introduced. | PgMC | B
28 | Baseline | Step I | Main Plot – Redefining Diamond Plot Boundaries | Page #93–95 – Main Plot: Re-defining Diamond Plot Boundaries | MP | Confirm the approach for plaza access, tower entrances, and pedestrian movement to ensure consistency with the approved masterplan principles. | PgMC | B
29 | Baseline | Step I | Main Plot – Redefining Diamond Plot Boundaries | Page #93–95 – Main Plot: Re-defining Diamond Plot Boundaries | MP | Identify outstanding workshop actions and stakeholder approvals required prior to freezing revised plot boundaries. | PgMC | B
30 | Baseline | Step I | Main Plot – Redefining Diamond Plot Boundaries | Page #93–95 – Main Plot: Re-defining Diamond Plot Boundaries | MP | Provide a detailed comparison between CMP and revised plot boundaries, including affected plot areas, ownership changes, GFA implications, and impacts on adjacent assets to ensure full traceability before design freeze. | PgMC | B
31 | Baseline | Step I | Main Plot - Undercroft Diagrids & Unique Parcel Na |  | MP | Provide a clear mapping matrix between existing CMP parcel names and revised parcel naming to maintain consistency across future DMP submissions. | PgMC | B
32 | Baseline | Step I | Main Plot - Undercroft Diagrids & Unique Parcel Na |  | MP | Clarify the planning rationale and implications of revised undercroft diagrid arrangements on parcel organization and development strategy. | PgMC | B
33 | Baseline | Step I | Main Plot - Undercroft Diagrids & Unique Parcel Na |  | MP | Confirm that workshop-agreed parcel naming and undercroft assumptions are consistently reflected across all disciplines. | PgMC | B
34 | Baseline | Step I | Main Plot - Undercroft Diagrids & Unique Parcel Na |  | MP | Identify any outstanding stakeholder dependencies or unresolved interfaces associated with revised undercroft arrangements. | PgMC | B
35 | Baseline | Step I | Main Plot - Undercroft Diagrids & Unique Parcel Na |  | MP | Provide a consolidated impact summary of affected parcels, including GFA and planning implications prior to progression into subsequent DMP stages. | PgMC | B
36 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #89 DCP interface – Mitigation scenario | District Cooling | As long as all pumps will be installed within the first floor to reduce the overall chillers yard width, a high-level floor plan layout for the DCP first floor is required, showing the arrangement of primary, secondary, condensing pumps, and auxiliary equipment to properly evaluate the proposed overall DCP width and the 3.0 m setbacks. | Ahmed Rakha | C
37 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #89 DCP interface – Mitigation scenario | District Cooling | Box dimensions layout according to the DCP capacity is required for the DCP basement floor, ensuring all grey water plant, treatment plants, and storage tanks (grey, TSE, mixed water) can be accommodated within a single basement level and don't require an additional basement level. | Ahmed Rakha | C
38 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #90 DCP interface – Mitigation scenario | District Cooling | The total required capacity for DCP-04 shall be mentioned based on the most updated GFA, phasing strategy, and master district cooling network arrangement. | Ahmed Rakha | B
39 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #90 DCP interface – Mitigation scenario | District Cooling | Please confirm 7x (odd arrangement) chillers' row arrangement is suitable for the series counterflow arrangement approach. | Ahmed Rakha | B
40 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | MCMP Comments Tracker | Infrastructure | comment no. 1 in the MCMP comments tracker (both Security Building No 3 and PSS Studies) still open, to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
41 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #92–94 – Security Building 03 Integration | MP | Confirm the agreed workshop assumptions for Security Building 03 and PSS integration and ensure consistency across all affected workstreams. | PgMC | B
42 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #92–94 – Security Building 03 Integration | MP | Provide a consolidated summary of impacts on adjacent plots, circulation, and public realm interfaces arising from SB#03 and PSS integration. | PgMC | B
43 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #92–94 – Security Building 03 Integration | MP | Clarify dependencies and required stakeholder inputs related to Security Building 03 integration to avoid downstream masterplan modifications. | PgMC | B
44 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #92–94 – Security Building 03 Integration | MP | Demonstrate alignment between the proposed integration approach and approved masterplan principles, including access, operational interfaces, and land-use strategy. | PgMC | C
45 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #92–94 – Security Building 03 Integration | MP | Provide a comparison between original and revised configurations, including affected plot areas, GFA impacts, and associated planning implications prior to design freeze. | PgMC | C
46 | Baseline | Step I | Main Plot – Integration of Security Building 03 & | Page #92–94 – Security Building 03 Integration | MP | Identify all workshop action items that remain open and clearly define ownership for closure in subsequent DMP stages | PgMC | B
47 | Baseline | Step I | Civic Site – Parking Self Sufficiency of Plots |  | Mobility | What is the parking sufficiency assessment for the various parcels within the Main Plot? Please include. | HR | C
48 | Baseline | Step I | Civic Site – Parking Self Sufficiency of Plots |  | MP | Clarify the assumptions adopted during the workshop regarding shared parking versus self-sufficient plot strategies and demonstrate alignment across all civic plots. | PGMC | B
49 | Baseline | Step I | Civic Site – Parking Self Sufficiency of Plots |  | MP | Provide a consolidated plot-by-plot summary identifying parking demand, supply, deficits/surplus, and reliance on shared facilities. | PGMC | B
50 | Baseline | Step I | Civic Site – Parking Self Sufficiency of Plots |  | MP | Confirm dependencies on external parking provisions and identify any associated operational or phasing implications. | PGMC | B
51 | Baseline | Step I | Civic Site – Parking Self Sufficiency of Plots |  | MP | Demonstrate consistency between parking assumptions and the latest mobility strategy, public transport assumptions, and revised RCMC inputs. | PGMC | B
52 | Baseline | Step I | Civic Site – Parking Self Sufficiency of Plots |  | MP | Provide a clear comparison between CMP parking assumptions and revised DMP assumptions, including impacts on plot functionality and development capacity. | PGMC | C
53 | Baseline | Step I | MP Key | MCMP Comments Tracker (Topography Impact) | Infrastructure | Comment no. 1 in the MCMP comments tracker (Topography Impact Study) still open, to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
54 | Baseline | Step I | MP Key | MP Key Assumptions – General | MP | Provide a consolidated register of all planning assumptions adopted during the workshop and identify confirmed versus pending items requiring stakeholder direction. |  | B
55 | Baseline | Step I | MP Key | MP Key Assumptions – AlHaram Boundary / Development Brief | MP | Clarify the impact of revised AlHaram boundary assumptions on adjacent plots, development capacity, and interface requirements. |  | B
56 | Baseline | Step I | MP Key | MP Key Assumptions – New Plot Names | MP | Provide a mapping matrix between previous and revised plot naming conventions to ensure consistency across all disciplines and future submissions. |  | B
57 | Baseline | Step I | MP Key | MP Key Assumptions – Existing Mosques to be Preserved | MP | Confirm preservation strategy and identify impacts on surrounding plot configuration, circulation, and masterplan assumptions. |  | B
58 | Baseline | Step I | MP Key | MP Key Assumptions – General | MP | Provide a comparison between CMP assumptions and revised DMP assumptions, including planning implications and downstream impacts prior to design freeze. |  | C
59 | Baseline | Step I | VA Integration Assumptions - Floor to Floor Tower Heights |  | MP | Provide a consolidated register of all Value Engineering assumptions adopted during the workshop and distinguish approved assumptions from pending items. |  | B
60 | Baseline | Step I | VA Integration Assumptions - Floor to Floor Tower Heights |  | MP | Demonstrate the impact of proposed VA measures on development capacity, GFA distribution, and approved masterplan principles. |  | B
61 | Baseline | Step I | VA Integration Assumptions - Floor to Floor Tower Heights |  | MP | Clarify the planning rationale supporting revised floor-to-floor heights and tower optimization assumptions and identify any resulting constraints. |  | B
62 | Baseline | Step I | VA Integration Assumptions - Floor to Floor Tower Heights |  | MP | Confirm that proposed VA assumptions have been coordinated across architecture, structure, MEP, and infrastructure disciplines. |  | B
63 | Baseline | Step I | VA Integration Assumptions - Floor to Floor Tower Heights |  | MP | Provide a comparison matrix between original and revised assumptions, including impacts on tower configurations, plot development strategy, and planning implications. |  | B
64 | Baseline | Step I | VA Integration Assumptions - Floor to Floor Tower Heights |  | MP | Identify all outstanding stakeholder decisions and workshop actions required prior to progressing into subsequent DMP stages. |  | B
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## MOBILITY
REVIEW AND COMMENT SHEET |  |  | WorkStream: | MOBILITY
| Submission: | Baseline | Revision: | V01 | Doc Ref.: |  | Prepared by: |  |  |  | Date:
COMMENT IDENTIFICATION | [5 empty] | ROUND 1 – CLIENT / RUA |  |  |  | ROUND 1 – DESIGNER RESPONSE |  |  | ROUND 2 – CLIENT / RUA |  |  |  | ROUND 2 – DESIGNER RESPONSE |  |  | ROUND 3 – CLIENT / RUA |  |  |  | ROUND 3 – DESIGNER RESPONSE |  |  | FINAL (CLIENT ONLY)
No. | Submission | Milestone | Topic | Doc / Drawing Ref. | Discipline | R1 – RUA Comment | R1 – Comment By | R1 – Status (CLIENT ONLY) | CRITICAL | R1 – Designer Response | R1 – Response By | R1 – Response Date | R2 – RUA Comment | R2 – Comment By | R2 – Status (CLIENT ONLY) | CRITICAL | R2 – Designer Response | R2 – Response By | R2 – Response Date | R3 – RUA Comment | R3 – Comment By | R3 – Status (CLIENT ONLY) | CRITICAL | R3 – Designer Response | R3 – Response By | R3 – Response Date | Final Status (CLIENT ONLY) | CRITICAL | Remarks / Notes
1 | Baseline | Step I | Ring Road Connector integration strategy | Page # 173 Optioneering & Further Development | Mobility | 1st Ring Road level (312 m) seems to be Ellipsoidal level. Final layout is subjected to Detailed Topographical Survey (Orthometric level) levels. | NNF | B
2 | Baseline | Step I | Ring Road Connector integration strategy | Page # 173 Optioneering & Further Development | Mobility | Proposed Option 01 and 02 to be checked for intended vehicular swept path, to see impact of development | NNF | B
3 | Baseline | Step I | Ring Road Connector integration strategy | Page # 176 Section of Option 02 (with Tie in lvl +317m) | Mobility | Proposed Section A-A' does not match with horizontal layout at Page # 173 | NNF | B
4 | Baseline | Step I | Ring Road Connector integration strategy | Page # 176 Key Action Slide | Mobility | Carriageway width is as per RCMC Option 2, which was studied in detailed during CMP Stage (below screen shot) | NNF | A
5 | Baseline | Step I | Ring Road Connector integration strategy | General Comment | Mobility | Full slide deck will be required for BoD Meeting. Concept Design of RR connection with all relevant disciplines's drawings/ documents. | NNF
6 | Baseline | Step I | Ring Road Connector integration strategy | Page # 176 Key Action Slide | Mobility | For the RR connector Section AA Option 2, how is the proposed ring road level of +324m connecting with existing 1st RR level of +312m (or +308)? There will be a difference of 12m requiring very steep ramp to connect the short distance. | HR | B
7 | Baseline | Step I | Ring Road Connector integration strategy | General Comment | Mobility | What will be changes under 2nd RR at King Fahd Road? Will it be signalized junction? | NNF | B
8 | Baseline | Step I | Ring Road Connector integration strategy | MCMP Comments tracker | Infrastructure | comment no. 7 in the MCMP comments tracker still open, to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
9 | Baseline | Step I | Ring Road Connector integration strategy | Ring Road Connector Integration Strategy – General | MP | Confirm the preferred Ring Road Connector option agreed during the workshop and identify assumptions adopted for progression into DMP. | PGMG | B
10 | Baseline | Step I | Ring Road Connector integration strategy | Ring Road Connector Integration Strategy – General | MP | Provide a consolidated summary of impacts on adjacent plots, development parcels, and public realm interfaces resulting from the selected RR alignment. | PGMG | B
11 | Baseline | Step I | Ring Road Connector integration strategy | Ring Road Connector Integration Strategy – General | MP | Clarify interfaces and dependencies with parallel workstreams including infrastructure, utilities, crowd movement, and constructability. | PGMG | B
12 | Baseline | Step I | Ring Road Connector integration strategy | Ring Road Connector Integration Strategy – General | MP | Demonstrate alignment between the proposed RR strategy and the latest stakeholder inputs and mobility assumptions. | PGMG | B
13 | Baseline | Step I | Ring Road Connector integration strategy | Ring Road Connector Integration Strategy – General | MP | Provide a comparison matrix between CMP and revised RR configurations, including affected plots, GFA impacts, and planning implications prior to design freeze. | PGMG | B
14 | Baseline | Step I | Ring Road Connector integration strategy | Ring Road Connector Integration Strategy – General | MP | Identify temporary assumptions pending completion of supporting studies and assess potential impacts if revised. | PGMG | B
15 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 184 Shaeb Amer Bus Station Test fit | Mobility | Layout to show RR connection to fully understand access points | NNF | C
16 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 184 Shaeb Amer Bus Station Test fit | Mobility | Number of lanes per access points, to be in line with Pre-concept (where 3+3 lanes are advised) | NNF | C
17 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 184 Shaeb Amer Bus Station Test fit | Mobility | Test fit to show columns locations to work out available space for space proofing | NNF | C
18 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 188 Shaeb Amer Bus Station overlay with Temporary Bus Station | Mobility | What will be available construction zone (along with buffer) once Temporary bus station is in operation and Permanent bus station works are started? | NNF | B
19 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 188 Shaeb Amer Bus Station overlay with Temporary Bus Station | Mobility | Phasing of Temporary bus station access via King Fahd to be fully studied with permanent work's phasing (Bus station and RR connection) | NNF | B
20 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 184 Shaeb Amer Bus Station Test fit | Mobility | SAE station capacity is 91,800 pp/hr equivalent to 1,224 buses/hr (ie. 102 active bays). Is it adequate to have only 1 bus ingress and 1 bus egress - is there an alternative route in case one access gets congested? How does the layout cater to buses entering from AlMasjid AlHaram Road or buses exiting to King Fahd tunnel? | HR | C
21 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 184 Shaeb Amer Bus Station Testfit | Mobility | Substation dedicated to serving bus station should be included in station footprint. Have the revised bus layout footprint considered incorporation of other MEP rooms, ancillary areas and back of house services and vertical circulation (lifts, escalators, staircases) areas? | HR | C
22 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 193 Shaeb Amer Bus Station overlay with Ring Road Connector | Mobility | RR connector tie-in levels subject to Detailed Topographical Survey | NNF | C
23 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 194 & 195 Shaeb Amer Bus Station overlay with Ring Road Connector - Constructability Inputs | Mobility | Both Temporary Bridge and Pedestrian Access show +307m level. Is it correct? Are pedestrian going over the bridge or under the bridge? | NNF | C
24 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 184 Shaeb Amer Bus Station Testfit | Mobility | In CMP, there were 102 active bays supported by 200 layover bays (ie. ratio of 1:2). We understood earlier that this ratio is to allow for quick bus turnaround with bus headways at every 5min intervals. However, in the BDMP report due to the reduction in bus station footprint, the number of active bus bays has been revised to 123 active bus bays with only 36 layover bays (ie. ratio reduced to 1:3.4). Please revert with confirmation that the revised ratio can support the bus operations at such high frequency of 1,224 buses per hour. | HR | C
25 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 193 Shaeb Amer Bus Station overlay with Ring Road Connector | Mobility | What are these "permanent Tunnels"? | NNF | B
26 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 184 Shaeb Amer Bus Station Testfit | Mobility | Please confirm whether the bus station upper concourse floor area are still aligned with LOS C (ie. 0.65 - 0.93m2/person) for sizing of passenger waiting areas. Does the revised station footprint accommodate this requirement? | HR | C
27 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 184 Shaeb Amer Bus Station Testfit | Mobility | Noted that the ring road connector crossing at +322.5 level which is above the bus concourse at +307. Wouldn't this new road (+322.5) connecting to 1RR (+312) level be impacting on the headroom clearance of the bus concourse? | HR | C
28 | Baseline | Step I | Temporary & Permanent Bus Stations | Page # 197 Phase 1 - Temporary Bus Station Operational | Mobility | The sectional drawing of Shaeb Amer bus station shows pedestrian access (+307) blocking the route of bus ingress/egress (blue shaded area) from the temporary bus station (yellow shaded area). Please amend. | HR | C
29 | Baseline | Step I | Temporary & Permanent Bus Stations | Page #186 Shaeb Amer Bus Station Relocation | Mobility | What are the 2nd RR levels (over and under bridge) in relation with excavated Zamzam plaza level of 307m. | NNF | B
30 | Baseline | Step I | Temporary & Permanent Bus Stations | Page #178 Expanded JAK Bus Station (Permanent) | Mobility | For revised JAK bus station layout ie. inverted bus concourse, new bus ingress and egress is proposed to be tapped from the 2nd RR elevated road level, please seek RCMC's concurrence expressly before proceeding with the concept design revision. | HR | C
31 | Baseline | Step I | Temporary & Permanent Bus Stations | Page #178 Expanded JAK Bus Station (Permanent) | Mobility | For all bus stations, please ensure the quantity and width of bus lanes for bus ingress and egress are adequate to support the high frequency bus operations of approximately 930 buses (JAK), 1,224 buses (SAE) and 360 buses (Jarwal) per hour. | HR | C
32 | Baseline | Step I | Temporary & Permanent Bus Stations | Page #178 Expanded JAK Bus Station (Permanent) | Mobility | For the inverted JAK bus station proposal, please ensure that all routes corresponding to the various bus operations are able to access the bus concourse at the upper level, particularly pertaining to the inner-city bus routes, the 7 Grand Axes and to/from Hajj sites. Please provide another bus ingress access points via Omar Ibn Abdul Aziz road. | HR | C
33 | Baseline | Step I | Temporary & Permanent Bus Stations | Page #54 Topic 1: Impact of SGS Guidelines - MCMP - Jarwal Plaza Option 1 | Mobility | Noted that there is a new elevated plaza level added above the proposed Jarwal plaza. Based on RCMC's latest crowd projection (Jan 2026), the Crowd team has reported that Jarwal bus station needs to cater to increased crowd flow larger than what the station footprint can accommodate - is the new elevated plaza able to accommodate this increase in spillover crowds? | HR | C
34 | Baseline | Step I | Temporary & Permanent Bus Stations | Permanent Bus Station- Utility Assessment | Infrastructure | Utility assessment with appropriate (as applicable) demand calculations and networks, plants, corridors update to be addressed and closed in the appropriate stage of the DMP without impacting any subsequent dependent stage. | PgMC | C
35 | Baseline | Step I | Temporary & Permanent Bus Stations | Temporary & Permanent Bus Stations – General | MP | Have the operational assumptions for transition from temporary to permanent bus station operations been validated, and are there any impacts on circulation, accessibility, and adjacent developments during phased implementation? | PgMC | C
36 | Baseline | Step I | Temporary & Permanent Bus Stations | Temporary & Permanent Bus Stations – General | MP | What are the downstream impacts if revised bus demand, crowd projections, or active bay requirements exceed the current planning assumptions? | PgMC | C
37 | Baseline | Step I | Temporary & Permanent Bus Stations | Temporary & Permanent Bus Stations – General | MP | Have all workshop agreements and stakeholder decisions related to Ring Road (RR) connectivity, bus operations, and phasing strategy been obtained, and are any remaining items required to be closed prior to progression into the next DMP stage? | PgMC | B
38 | Baseline | Step I | Temporary & Permanent Bus Stations | Temporary & Permanent Bus Stations – General | MP | Have all key stakeholder decisions related to bus operations, Ring Road connectivity, phasing strategy, and station functionality been formally agreed, and are any unresolved governance items affecting progression into subsequent DMP stages? | PgMC | C
39 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page # 205 Topic 3 RCMC New Metro Alignment - Al Sulaymaniyah Metro Station Impact | Mobility | Please assess and provide technical justifications for the placement of Al Sulaymaniyah station in terms of transport planning considerations ie. comparing the acceptable distance between metro stations against international benchmarks and train operations (ie. distance required for trains to accelerate, cruising and braking before arriving into the next station) e.g. energy consumption due to frequent start and stops. | HR | C
40 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page # 205 Topic 3 RCMC New Metro Alignment - Al Sulaymaniyah Metro Station Impact | Mobility | BDMP report requested further info on potential station entry and exit points and queuing requirements. In the previous CMP stage, these were provided by the Consortium based on stated assumptions. Please refer CMP report Crowd Management section ie. Sulaymaniyah metro station to accommodate 117,000 pp/hour (incl 30 min queuing). Queuing requirements (area in m2) can be derived from this assumption. | HR | C
41 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page # 205 Topic 3 RCMC New Metro Alignment - Al Sulaymaniyah Metro Station Impact | Mobility | Please provide the justification for placement of Al Sulaymaniyah station in terms of projected population catchment within its serving radius. Compare this against international benchmarks for minimum TOD population catchment to justify placement of new metro stations. | HR | C
42 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page # 205 Topic 3 RCMC New Metro Alignment - Al Sulaymaniyah Metro Station Impact | Mobility | The site is already served by the proposed PRT system. Adding a metro station over a planned light rail system violates “one corridor, one trunk mode” principles and creates competing services for the same population catchment which in turn suggest inefficient infrastructure spending. This proposition will not be defensible when taken up to higher management. | HR | C
43 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page # 204 Topic 3 RCMC New Metro Alignment - CMP vs DMP - Metro Alignment Difference | Mobility | Metro Line B text to read "Metro Line C" and Metro Line C text to read "Metro Line B" | NNF | B
44 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page # 207 Topic 3 RCMC New Metro Alignment - Integration of Al Sulaymaniyah Station | Mobility | In terms of Crowd Safety, metro station configuration with limited surface dispersal may create non-compliance with crowd management standards and evacuation modeling as per NFPA 130 during mass gathering scenarios. This is since more than half of the serving coverage is mountainous terrain might make it difficult to create assembly spaces. Also, in high density mass gatherings, placing main transport hubs close together may create a fragmented crowd management environment by violating the principles of linear flow which is essential for safety. This is because peak scenarios rely on streaming pilgrims in one direction to prevent crush incidents and effective management require long reservoir spaces between nodes to absorb surges. Please address these concerns. | HR | C
45 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page # 207 Topic 3 RCMC New Metro Alignment - Integration of Al Sulaymaniyah Station | Mobility | It is not clear which category of the public gets to benefit from this urban connection to Sulaymaniyah metro station. In terms of transport connectivity, pilgrims can simply take the PRT from Marwa station closest to Haram to get to Sulaymaniyah area instead of walking more than 1km to get to the remote metro station. | HR | C
46 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page # 207 Topic 3 RCMC New Metro Alignment - Integration of Al Sulaymaniyah Station | Mobility | The station is located along the slopes of the mountainous terrain in Sulaymaniyah. This will inform on the method of station box construction and the site enabling works involved e.g. rock cutting and safety considerations. Any assessment of cost-benefit analysis shall include these considerations. | HR | C
47 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page #203–205 – Latest RCMC Metro Network & Al Sulaymaniyah Station | MP | Confirm the preferred metro alignment and Al Sulaymaniyah Station integration approach agreed during the workshop for progression into DMP. | PgMC | B
48 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page #203–205 – Latest RCMC Metro Network & Al Sulaymaniyah Station | MP | Provide a consolidated summary of impacts on adjacent plots, public realm interfaces, and development assumptions resulting from the updated metro network. | PgMC | B
49 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page #203–205 – Latest RCMC Metro Network & Al Sulaymaniyah Station | MP | Clarify dependencies on RCMC inputs and identify assumptions adopted pending receipt of final metro information. | PgMC | B
50 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page #203–205 – Latest RCMC Metro Network & Al Sulaymaniyah Station | MP | Demonstrate alignment between the updated metro strategy and mobility, crowd movement, and access assumptions across the masterplan. | PgMC | B
51 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page #203–205 – Latest RCMC Metro Network & Al Sulaymaniyah Station | MP | Provide a comparison matrix between CMP and revised metro configurations, including impacts on affected plots and planning implications. | PgMC | C
52 | Baseline | Step I | Latest RCMC Metro Network & Al Sulaymaniyah Station | Page #203–205 – Latest RCMC Metro Network & Al Sulaymaniyah Station | MP | Confirm outstanding stakeholder actions and workshop decisions required prior to design freeze | PgMC | C
53 | Baseline | Step I | Jarwal Multimodal Hub | Utility Assessment | Infrastructure | - Provide utility demand calculation details (tables indicating plot No, GFA, land use, demand rate, demand). Impact on solid waste demand to be provided and included. - Layout and sizing of the utility networks, plants, stations and corridors to be updated in the upcoming stage. - Comments to be addressed and closed within the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
54 | Baseline | Step I | Jarwal Multimodal Hub | Jarwal Multimodal Hub – General | MP | Confirm the preferred Jarwal Multimodal Hub strategy agreed during the workshop and identify assumptions adopted for progression into DMP. | PgMC | B
55 | Baseline | Step I | Jarwal Multimodal Hub | Jarwal Multimodal Hub – General | MP | Clarify interfaces and dependencies with metro, bus, crowd movement, and surrounding transport systems to ensure alignment across workstreams. | PgMC | B
56 | Baseline | Step I | Jarwal Multimodal Hub | Jarwal Multimodal Hub – General | MP | Provide a comparison between CMP and revised hub assumptions, including impacts on plot development, circulation, and planning implications. | PgMC | C
57 | Baseline | Step I | Jarwal Multimodal Hub | Jarwal Multimodal Hub – General | MP | Provide a comparison between CMP and revised hub assumptions, including impacts on plot development, circulation, and planning implications. | PgMC | C
58 | Baseline | Step I | Paramobility Network | Page # 218 Topic 5 - Paramobility Network | Mobility | Before coordinating with RCMC, RUA will first need to see the revised masterplan layout incorporating the paramobility route and the spatial provision for all associated amenities. Any paramobility proposal shall also be reflected in conjunction with Topic 3: Jabal AlKaaba Plaza & Heritage Plaza. | HR | C
59 | Baseline | Step I | Paramobility Network | Page #218 – Topic 5: Paramobility Network | MP | Confirm the preferred paramobility strategy and assumptions agreed during the workshop for progression into DMP. | PgMC | B
60 | Baseline | Step I | Paramobility Network | Page #218 – Topic 5: Paramobility Network | MP | Demonstrate alignment between the proposed paramobility network and pedestrian movement, crowd management, and public transport strategies. | PgMC | B
61 | Baseline | Step I | Paramobility Network | Page #218 – Topic 5: Paramobility Network | MP | Provide a consolidated impact assessment identifying affected plots, public realm interfaces, and planning implications arising from the proposed paramobility network. | PgMC | C
62 | Baseline | Step I | Paramobility Network | Page #218 – Topic 5: Paramobility Network | MP | Identify outstanding stakeholder actions and assumptions pending confirmation prior to progression into subsequent DMP stages. | PgMC | B
63 | Baseline | Step I | Parking Assumptions | Topic 06 – Parking Assumptions | MP | Confirm the approved parking strategy and rates with RCMC and identify assumptions adopted for progression into DMP. | PgMC | C
64 | Baseline | Step I | Parking Assumptions | Topic 06 – Parking Assumptions | MP | Provide a consolidated parking demand and supply summary by land use and plot, including deficit/surplus assessment. | PgMC | B
65 | Baseline | Step I | Parking Assumptions | Topic 06 – Parking Assumptions | MP | Demonstrate alignment between parking assumptions and the latest public transport strategy, including metro, bus, and paramobility networks. | PgMC | B
66 | Baseline | Step I | Parking Assumptions | Topic 06 – Parking Assumptions | MP | Clarify assumptions related to shared parking provisions and identify operational dependencies between plots. | PgMC | B
67 | Baseline | Step I | Parking Assumptions | Topic 06 – Parking Assumptions | MP | Identify outstanding stakeholder actions and workshop decisions required prior to progression into subsequent DMP stages. | PgMC | B
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## PUBLIC_REALM
REVIEW AND COMMENT SHEET |  |  | WorkStream: | PUBLIC REALM
| Submission: | Baseline | Revision: | V01 | Doc Ref.: |  | Prepared by: |  |  |  | Date:
COMMENT IDENTIFICATION | [5 empty] | ROUND 1 – CLIENT / RUA |  |  |  | ROUND 1 – DESIGNER RESPONSE |  |  | ROUND 2 – CLIENT / RUA |  |  |  | ROUND 2 – DESIGNER RESPONSE |  |  | ROUND 3 – CLIENT / RUA |  |  |  | ROUND 3 – DESIGNER RESPONSE |  |  | FINAL (CLIENT ONLY)
No. | Submission | Milestone | Topic | Doc / Drawing Ref. | Discipline | R1 – RUA Comment | R1 – Comment By | R1 – Status (CLIENT ONLY) | CRITICAL | R1 – Designer Response | R1 – Response By | R1 – Response Date | R2 – RUA Comment | R2 – Comment By | R2 – Status (CLIENT ONLY) | CRITICAL | R2 – Designer Response | R2 – Response By | R2 – Response Date | R3 – RUA Comment | R3 – Comment By | R3 – Status (CLIENT ONLY) | CRITICAL | R3 – Designer Response | R3 – Response By | R3 – Response Date | Final Status (CLIENT ONLY) | CRITICAL | Remarks / Notes
1 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Provide confirmation of the agreed road slope criteria and any authority exceptions adopted during the workshop to ensure progression into DMP. | PgMC | C
2 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Demonstrate impacts of revised slope conditions on emergency access routes, fire response requirements, and adjacent plot accessibility. | PgMC | B
3 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Clarify interfaces between revised road geometry and crowd movement/public realm strategies to avoid downstream design conflicts. | PgMC | B
4 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Confirm the revised fire station distribution strategy and identify dependencies on response time assumptions. | PgMC | B
5 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Identify outstanding stakeholder actions and workshop decisions requiring closure prior to progression into subsequent DMP stages. | PgMC | B
6 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Confirm the agreed road slope criteria and any authority exceptions adopted during the workshop to ensure progression into DMP. | PgMC | B
7 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Demonstrate impacts of revised slope conditions on emergency access routes, fire response requirements, and adjacent plot accessibility. | PgMC | B
8 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Provide confirmation that the revised road geometry (horizontal and vertical alignment, turning radii, and transition areas) has been coordinated with emergency access, mobility requirements, and adjacent plot interfaces. | PgMC | B
9 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Provide a detailed summary of road slope percentages, including lengths of segments exceeding target thresholds, and confirm compliance with authority requirements and emergency access criteria. | PgMC | B
10 | Baseline | Step I | Roads, Slopes revisions & Fire Life Safety | Topic 01 – Roads, Slopes & Fire Life Safety | MP | Confirm road slope percentages and identify any segments exceeding agreed design criteria, including proposed mitigation measures. | PgMC | B
11 | Baseline | Step I | Redistribution of Fire Stations & new response time | Redistribution of Fire Stations & Response Time – General | MP | Provide validation that the revised fire station distribution achieves the required response time targets across all development zones. | PgMC | C
12 | Baseline | Step I | Redistribution of Fire Stations & new response time | Redistribution of Fire Stations & Response Time – General | MP | Demonstrate the impact of revised fire station locations on emergency access routes, road hierarchy, and adjacent developments. | PgMC | B
13 | Baseline | Step I | Redistribution of Fire Stations & new response time | Redistribution of Fire Stations & Response Time – General | MP | Confirm assumptions and stakeholder agreements adopted during the workshop and identify any outstanding items pending authority confirmation. | PgMC | B
14 | Baseline | Step I | Redistribution of Fire Stations & new response time | Redistribution of Fire Stations & Response Time – General | MP | Provide a coverage map identifying any areas with reduced fire service accessibility resulting from the revised fire station distribution and proposed mitigation measures. | PgMC | B
15 | Baseline | Step I | Redistribution of Fire Stations & new response time | Redistribution of Fire Stations & Response Time – General | MP | Confirm all workshop-agreed assumptions for revised fire station locations and response time criteria, and identify any open items requiring stakeholder or authority confirmation prior to progression into subsequent DMP stages. | PgMC | B
16 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Implication Assessment | Mobility | Iem # B - Please elaborate on Road Tunnelling with respect to water table and Jabal Al Kaaba bus station access | NNF | C
17 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Implication Assessment | Mobility | Item # E - Please advise on road leading to undercroft. Is it at-grade or below ground? | NNF | B
18 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 244 Underground Vehicles Circulation | Mobility | Please elaborate more on underground junction by using 3D view, in relation with ground water table/ vehicular and non-vehicular movements | NNF | C
19 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Topic 3: Jabal AlKaaba Road Extension Assessment | Mobility | In the revised JAK bus station concept, there is pedestrian access via overhead bridge across the existing JAK road to the upper bus passenger area but this was not reflected in the JAK Road extension layout. Please indicate this pedestrian access to the upper level bus station in the layout. | HR | C
20 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Topic 3: Jabal AlKaaba Road Extension Assessment | Mobility | In the vehicles circulation diagram, there is only 1 bus access into JAK bus station. What about incoming bus movement from the 2nd RR exit via Omar Ibn Abdulaziz Road - how will buses from this exit access the bus station? Why is the 1 bus access annotated as "flyover" when the bus concourse is at grade? Please also indicate the point of bus egress. | HR | C
21 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Topic 3: Jabal AlKaaba Road Extension Assessment | Mobility | Revised Station Capacity is 70,125 pp/hr (previously 31,500 pp/hr). Since external queuing capacity is assumed to be 50% of station capacity, 50% of 70,125 is 35,065 pp/hr. Total crowd flow projection for JAK is 105,190 pp/hr (previous 47,250 pp/hr). Based on LOS D ie. 0.65m2/pax, the required external queuing area will be 22,790m2. This area needs to be indicated at the elevated plaza area. | HR | C
22 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Topic 3: Jabal AlKaaba Road Extension Assessment | Mobility | The pedestrian circulation diagram shows the assembly point for security building 2 located at junction between JAK and Omar Ibn Abdulaziz road. However, under Topic 5 the assembly area is shown to be located directly in front of security building 2 (pg 267). Which is the correct location for the security building assembly area? | HR | C
23 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Topic 3: Jabal AlKaaba Road Extension Assessment | Mobility | Pedestrian circulation should also indicate the access into the bus stations - JAK & Jarwal to be from the elevated pedestrian spine level. | HR | C
24 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Topic 3: Jabal AlKaaba Road Extension Assessment - JAK Plaza and Heritage Plaza | Mobility | Annotation is incorrect, it should be Jabal AlKaaba bus station, not Al Byari. Have the PRT station placement along JAK Road (as per main plot standalone scenario) and any required rail setback been taken into consideration? | HR | C
25 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Topic 3: Jabal AlKaaba Road Extension Assessment - JAK Plaza and Heritage Plaza | Mobility | It is noted that the purple shaded areas indicates the elevated pedestrian level. If so, please indicate the vertical circulation nodes connecting the original datum or existing ground level to this proposed elevated level. | HR | C
26 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Page # 241 Topic 3: Jabal AlKaaba Road Extension Assessment - JAK Plaza and Heritage Plaza | Mobility | The PRT location shown in the section does not tally with the PRT study as per Main Plot standalone scenario. Please clarify. | HR | C
27 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | MCMP Comments Tracker (Umm AlQura and Jabal AlKaabah extension | Infrastructure | comment no. 1 in the MCMP comments tracker (Umm AlQura and Jabal AlKaabah extension study) still open, to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
28 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Umm AlQura Road & Jabal AlKaabah Road Extension – General | MP | Confirm that the revised road extension strategy complies with fire and emergency access requirements, including emergency vehicle movement and response time criteria. | PgMC | C
29 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Umm AlQura Road & Jabal AlKaabah Road Extension – General | MP | Demonstrate impacts of the revised road extensions on adjacent plots, public realm interfaces, and crowd movement strategies. | PgMC | B
30 | Baseline | Step I | Umm AlQura Road & Jabal AlKaabah Road Extension | Umm AlQura Road & Jabal AlKaabah Road Extension – General | MP | Confirm workshop-agreed assumptions and identify any outstanding stakeholder decisions related to road alignment and associated safety requirements. | PgMC | B
31 | Baseline | Step I | Re routing of Jarwal & Al Sulaymaniyah Pedestrian Spines | Page # 255 Topic 6: Re-routing of Pedestrian Spine - Pedestrian Spine Strategies | Mobility | There is no strong justification to locate Al Sulaymaniyah metro within the plot. The reason stated in the BDMP report, by doing so it is to create a termination point for the pedestrian axis, but if that is the case, wouldn't a PRT station already qualify as a transport node for axis termination? | HR | C
32 | Baseline | Step I | Re routing of Jarwal & Al Sulaymaniyah Pedestrian Spines | Page #255 Topic 6 – Re-routing of Pedestrian Spine | MP | Demonstrate impacts of the revised pedestrian spine alignment on crowd movement, pedestrian capacity, and adjacent plot accessibility. | PgMC | B
33 | Baseline | Step I | Re routing of Jarwal & Al Sulaymaniyah Pedestrian Spines | Page #255 Topic 6 – Re-routing of Pedestrian Spine | MP | Confirm workshop-agreed assumptions for the preferred pedestrian spine strategy and identify any outstanding stakeholder decisions. | PgMC | B
34 | Baseline | Step I | Re routing of Jarwal & Al Sulaymaniyah Pedestrian Spines | Page #255 Topic 6 – Re-routing of Pedestrian Spine | MP | Provide a comparison between CMP and revised pedestrian spine configurations, including impacts on public realm interfaces and development parcels. | PgMC | C
35 | Baseline | Step I | Re routing of Jarwal & Al Sulaymaniyah Pedestrian Spines | Page #255 Topic 6 – Re-routing of Pedestrian Spine | MP | Clarify integration between the revised pedestrian spine and metro, PRT, and surrounding mobility systems to ensure continuity of movement strategy. | PgMC | B
36 | Baseline | Step I | Re routing of Jarwal & Al Sulaymaniyah Pedestrian Spines | Page #255 Topic 6 – Re-routing of Pedestrian Spine | MP | Confirm that the revised pedestrian spine alignment reflects the outcomes of mobility, crowd movement, and masterplanning focus group discussions and identify any remaining open items requiring closure. | PgMC | B
37 | Baseline | Step I | Re routing of Jarwal & Al Sulaymaniyah Pedestrian Spines | Page #255 Topic 6 – Re-routing of Pedestrian Spine | MP | Provide a summary of workshop/focus group outcomes that informed the revised pedestrian spine strategy and clearly distinguish agreed items from assumptions pending stakeholder confirmation. | PgMC | B
38 | Baseline | Step I | Pedestrian Tunnel 02 Integration strategy | Pedestrian Tunnel 02 Integration Strategy – General | MP | Provide justification for the preferred Tunnel 02 integration strategy and demonstrate alignment with crowd movement requirements and overall pedestrian network objectives. | PgMC | C
39 | Baseline | Step I | Pedestrian Tunnel 02 Integration strategy | Pedestrian Tunnel 02 Integration Strategy – General | MP | Demonstrate impacts of Tunnel 02 integration on pedestrian capacity, movement continuity, and adjacent plot accessibility. | PgMC | B
40 | Baseline | Step I | Pedestrian Tunnel 02 Integration strategy | Pedestrian Tunnel 02 Integration Strategy – General | MP | Provide a summary of workshop/focus group outcomes that informed the Tunnel 02 strategy and clearly distinguish agreed items from assumptions pending stakeholder confirmation. | PgMC | B
41 | Baseline | Step I | Pedestrian Tunnel 02 Integration strategy | Pedestrian Tunnel 02 Integration Strategy – Workshop Outcome | MP | Provide a clear record of the workshop decision regarding Security Building 02 retention, Tunnel 02 mouth integration, Fan Station 02 relocation, and public realm strategy, including agreed direction and unresolved items requiring stakeholder alignment. | PgMC | C
42 | Baseline | Step I | AlHaram Entrance Gate Zone-16 integration | AlHaram Entrance Gate Zone-16 Integration – General | MP | Demonstrate that the proposed Gate Zone-16 integration strategy maintains crowd movement capacity and emergency evacuation performance requirements. | PgMC | C
43 | Baseline | Step I | AlHaram Entrance Gate Zone-16 integration | AlHaram Entrance Gate Zone-16 Integration – General | MP | Clarify interfaces between Gate Zone-16 and surrounding public realm, pedestrian routes, and adjacent development plots to ensure continuity of movement. | PgMC | B
44 | Baseline | Step I | AlHaram Entrance Gate Zone-16 integration | AlHaram Entrance Gate Zone-16 Integration – General | MP | Provide a summary of workshop/focus group outcomes that informed the Gate Zone-16 integration strategy and distinguish agreed items from assumptions pending stakeholder confirmation. | PgMC | B
45 | Baseline | Step I | AlHaram Entrance Gate Zone-16 integration | AlHaram Entrance Gate Zone-16 Integration – General | MP | Provide an impact assessment of the revised integration strategy on accessibility, operational requirements, and downstream masterplanning assumptions. | PgMC | B
46 | Baseline | Step I | AlHaram Entrance Gate Zone-16 integration | AlHaram Entrance Gate Zone-16 Integration – Workshop Outcome | MP | What are the implications if the proposed Gate Zone-16 integration strategy is not adopted, and how would alternative scenarios impact crowd movement, operational functionality, and adjacent development interfaces? | PgMC | C
47 | Baseline | Step I | Assessment of Latest RCMC Crowd Data | Page #283, Topic 07: Assessment of Latest RCMC Data - Station Review Capacity | Mobility | Based on RCMC's MCA Population Projection Year 2040, Jarwal's station capacity is 27,000 not 25,200. Please amend. | HR | B
48 | Baseline | Step I | Assessment of Latest RCMC Crowd Data | Page #283, Topic 07: Assessment of Latest RCMC Data - Station Review Capacity | Mobility | For JAK bus station, the passenger queuing figure is stated as 35,063 pp. If based on LOS D (0.65m2/pp), the queuing area within JAK station shall be 35,063 x 0.65 = 22,790 m2, whether this is the case. How is this passenger queuing figure within the station derived from the station capacity of 70,125 pp/h. Please clarify. | HR | B
49 | Baseline | Step I | Assessment of Latest RCMC Crowd Data | Topic 07 – Assessment of Latest RCMC Crowd Data | MP | Confirm that the revised RCMC crowd assumptions do not create downstream impacts on evacuation strategy, public realm sizing, and pedestrian infrastructure capacities. | PgMC | C
50 | Baseline | Step I | Assessment of Latest RCMC Crowd Data | Topic 07 – Assessment of Latest RCMC Crowd Data | MP | Provide a comparison matrix between CMP crowd assumptions and revised RCMC crowd data, including impacts on crowd movement strategy and planning assumptions. | PgMC | B
51 | Baseline | Step I | Assessment of Latest RCMC Crowd Data | Topic 07 – Assessment of Latest RCMC Crowd Data | MP | Provide a summary of workshop/focus group outcomes related to revised crowd assumptions and distinguish agreed items from assumptions pending stakeholder confirmation. | PgMC | B
52 | Baseline | Step I | Assessment of Latest RCMC Crowd Data | Topic 07 – Assessment of Latest RCMC Crowd Data | MP | Demonstrate the sensitivity of the proposed strategy to peak crowd scenarios and identify key risks if RCMC crowd projections are revised in subsequent stages. | PgMC | C
53 | Baseline | Step I | Assessment of Latest RCMC Crowd Data | Topic 07 – Assessment of Latest RCMC Crowd Data |  | Please clarify and validate the basis for applying the 1.4 reduction factor in the pedestrian tunnel capacity assessment and confirm whether this factor remains applicable under the revised crowd movement assumptions and tunnel configuration. | PgMC | C
54 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Confirm that the revised prayer facility requirements are based on the latest approved population and crowd assumptions and identify impacts on previously adopted planning assumptions. | PgMC | C
55 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Demonstrate impacts of revised prayer facility requirements on adjacent plots, public realm allocation, and pedestrian movement strategy. | PgMC | B
56 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Clarify the methodology and assumptions used to derive prayer facility demand, including peak-period requirements and operational considerations. | PgMC | B
57 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Provide a summary of workshop/focus group outcomes that informed the revised prayer facility strategy and distinguish agreed items from assumptions pending stakeholder confirmation. | PgMC | B
58 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Identify downstream impacts of revised prayer facility requirements on utilities, accessibility, and future development interfaces. | PgMC | B
59 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – Genera | MP | Has the 980K population assumption and 1.8 m² per worshipper planning criterion been coordinated and validated across all relevant disciplines (Crowd, Mobility, Public Realm, FLS, Infrastructure, and Masterplanning), and what are the downstream impacts if these assumptions are revised? | PgMC | C
60 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Has sensitivity testing been carried out for alternative population scenarios, and what are the impacts if the projected worshipper numbers exceed current planning assumptions? | PgMC | C
61 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Have revised prayer facility requirements been coordinated with Crowd, Mobility, Public Realm, Infrastructure, and FLS disciplines, and are there any conflicting assumptions currently identified? | PgMC | B
62 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | If prayer facility requirements increase during subsequent stages, what are the impacts on plot allocations, public realm areas, and surrounding development parcels? | PgMC | C
63 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Has the proposed prayer facility strategy been validated against peak prayer periods and crowd dispersal scenarios to confirm operational feasibility? | PgMC | B
64 | Baseline | Step I | Latest Prayer Facility Requirements | Latest Prayer Facility Requirements – General | MP | Are there any dependencies on external stakeholder or authority decisions that could alter the current prayer facility assumptions and associated planning strategy? | PgMC | B
65 | Baseline | Step I | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Public Realm VT Assumptions – General | MP | Please clarify and validate the basis used for sizing and quantity assumptions for escalators, stairs, and lifts and confirm alignment with latest crowd projections and peak movement scenarios. | PgMC | C
66 | Baseline | Step I | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Public Realm VT Assumptions – General | MP | Have VT assumptions been coordinated across Crowd, Mobility, Architecture, Public Realm, and FLS disciplines, and are any conflicting assumptions currently identified? | PgMC | B
67 | Baseline | Step I | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Public Realm VT Assumptions – General | MP | What are the impacts on crowd movement performance and LOS if VT demand exceeds current planning assumptions during peak periods? | PgMC | C
68 | Baseline | Step I | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Public Realm VT Assumptions – General | MP | Provide a summary of workshop/focus group outcomes that informed the VT strategy and distinguish agreed items from assumptions pending stakeholder confirmation. | PgMC | B
69 | Baseline | Step I | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Public Realm VT Assumptions – General | MP | Confirm interfaces between VT locations and surrounding pedestrian routes, tunnel access points, and public realm spaces to avoid downstream coordination conflicts. | PgMC | B
70 | Baseline | Step I | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Public Realm VT Assumptions – Genera | MP | Has sensitivity testing been undertaken for VT equipment outage scenarios (e.g., escalator/lift unavailability), and what are the impacts on pedestrian flow and emergency movement? | PgMC | B
71 | Baseline | Step I | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Public Realm VT Assumptions – Genera | MP | Please clarify and validate the basis for applying the 1.4 reduction factor and confirm whether its impact on effective pedestrian capacity has been coordinated with the VT strategy, including escalator, stair, and lift sizing assumptions. | PgMC | C
72 | Baseline | Step I | Public Realm VT Assumptions – Escalators, Stairs & Lifts | Public Realm VT Assumptions – Genera | MP | Please confirm that all stakeholder agreements and approvals related to VT assumptions, planning criteria, and associated movement strategies have been obtained. Any outstanding items requiring stakeholder confirmation shall be closed prior to progression into the next DMP stage. | PgMC | C
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## INFRASTRUCTURE
REVIEW AND COMMENT SHEET |  |  | WorkStream: | INFRASTRUCTURE
| Submission: | Baseline | Revision: | V01 | Doc Ref.: |  | Prepared by: |  |  |  | Date:
COMMENT IDENTIFICATION | [5 empty] | ROUND 1 – CLIENT / RUA |  |  |  | ROUND 1 – DESIGNER RESPONSE |  |  | ROUND 2 – CLIENT / RUA |  |  |  | ROUND 2 – DESIGNER RESPONSE |  |  | ROUND 3 – CLIENT / RUA |  |  |  | ROUND 3 – DESIGNER RESPONSE |  |  | FINAL (CLIENT ONLY)
No. | Submission | Milestone | Topic | Doc / Drawing Ref. | Discipline | R1 – RUA Comment | R1 – Comment By | R1 – Status (CLIENT ONLY) | CRITICAL | R1 – Designer Response | R1 – Response By | R1 – Response Date | R2 – RUA Comment | R2 – Comment By | R2 – Status (CLIENT ONLY) | CRITICAL | R2 – Designer Response | R2 – Response By | R2 – Response Date | R3 – RUA Comment | R3 – Comment By | R3 – Status (CLIENT ONLY) | CRITICAL | R3 – Designer Response | R3 – Response By | R3 – Response Date | Final Status (CLIENT ONLY) | CRITICAL | Remarks / Notes
1 | Baseline | Step I | Existing Utilities integration strategy | MCMP Comments tracker | Infrastructure | comments nos. 3, 4, 5, 6, 7, 8, 9, 10 and 11 in the MCMP comments tracker still open, to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
2 | Baseline | Step I | Existing Utilities integration strategy | CMP Comments Trackers | Infrastructure | THIS COMMENT IS NOT SPECIFICALLY RELATED TO THE Existing Utilities Integration Strategy Study of the MCMP, it is a general comment included to ensure that the large number of open comments in the CMP are well tracked, addressed and closed. All open comments in the CMP comments Trackers (50%, 100% Draft and 100% Final) to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
3 | Baseline | Step I | Existing Utilities integration strategy | Existing Utilities Integration Strategy – General | Infrastructure | Please confirm that the proposed utility integration strategy has been coordinated across all disciplines and identify any unresolved interface conflicts affecting downstream stages. | PgMC | C
4 | Baseline | Step I | Existing Utilities integration strategy | Existing Utilities Integration Strategy – General | Infrastructure | Demonstrate impacts of the proposed utility integration approach on plot development, underground structures, road corridors, and public realm interfaces. | PgMC | B
5 | Baseline | Step I | Existing Utilities integration strategy | Existing Utilities Integration Strategy – General | Infrastructure | What are the implications if existing utility diversion or protection assumptions change during subsequent stages, and what mitigation measures are proposed? | PgMC | C
6 | Baseline | Step I | Existing Utilities integration strategy | Existing Utilities Integration Strategy – General | Infrastructure | Provide a summary of workshop outcomes that informed the utility integration strategy and distinguish agreed items from assumptions pending stakeholder confirmation. | PgMC | B
7 | Baseline | Step I | Existing Utilities integration strategy | Existing Utilities Integration Strategy – General | Infrastructure | Have all stakeholder and authority confirmations related to existing utility interfaces been obtained, and are any remaining items required to be formally closed prior to progression into the next DMP stage? | PgMC | C
8 | Baseline | Step I | Existing Utilities integration strategy | Existing Utilities Integration Strategy – General | Infrastructure | Clarify any pending studies required to support the utility integration strategy and identify potential impacts on subsequent DMP stages if not completed. | PgMC | B
9 | Baseline | Step I | MOF Assets integration strategy | MCMP Comments Tracker | Infrastructure | comments nos. 1 and 5 in the MCMP comments tracker (comments 2, 3 and 4 are included in 1 - duplicated) still open, to be addressed and closed during the appropriate stage of the DMP without impacting any subsequent dependent stage. | ABA | B
10 | Baseline | Step I | MOF Assets integration strategy | MOF Assets Integration Strategy – General | Infrastructure | Please confirm that the proposed MOF asset integration strategy has been coordinated with all relevant disciplines and identify any unresolved interface conflicts affecting downstream stages. | PgMC | C
11 | Baseline | Step I | MOF Assets integration strategy | MOF Assets Integration Strategy – General | Infrastructure | Demonstrate impacts of the proposed MOF asset integration approach on plot development, utility corridors, underground structures, and public realm interfaces. |  | B
12 | Baseline | Step I | MOF Assets integration strategy | MOF Assets Integration Strategy – General | Infrastructure | Have all stakeholder agreements and MOF approvals been obtained, and are any remaining items required to be formally closed prior to progression into the next DMP stage? |  | C
13 | Baseline | Step I | MOF Assets integration strategy | MOF Assets Integration Strategy – General | Infrastructure | Please clarify any pending studies, investigations, or stakeholder inputs required to validate the MOF asset integration strategy and identify potential impacts if not completed. |  | B
14 | Baseline | Step I | MOF Assets integration strategy | MOF Assets Integration Strategy – General | Infrastructure | Provide a summary of workshop outcomes that informed the MOF asset integration strategy and distinguish agreed items from assumptions pending stakeholder confirmation. |  | B
15 | Baseline | Step I | Fan Stations Integration strategy | Fan Stations Integration Strategy – General | MP | Has the proposed fan station integration strategy been coordinated with all relevant disciplines, and are there any unresolved interface conflicts affecting downstream stages? | PgMC | C
16 | Baseline | Step I | Fan Stations Integration strategy | Fan Stations Integration Strategy – General | MP | What are the impacts of the proposed fan station locations on adjacent plots, underground structures, utility corridors, and public realm interfaces? | PgMC | B
17 | Baseline | Step I | Fan Stations Integration strategy | Fan Stations Integration Strategy – General | MP | If fan station locations or sizing requirements are revised during subsequent stages, what are the impacts on masterplan assumptions and associated infrastructure systems? | PgMC | C
18 | Baseline | Step I | Fan Stations Integration strategy | Fan Stations Integration Strategy – General | MP | Please clarify any pending studies, technical assessments, or stakeholder inputs required to validate the fan station integration strategy prior to progression into the next DMP stage. | PgMC | B
19 | Baseline | Step I | Fan Stations Integration strategy | Fan Stations Integration Strategy – General | MP | Have all stakeholder and authority agreements related to fan station requirements and locations been obtained, and are any outstanding items required to be formally closed prior to progression into the next DMP stage? | PgMC | C
20 | Baseline | Step I | MCA servicing strategy | MCA Servicing Strategy – General | MP | Has the proposed MCA servicing strategy been coordinated across all relevant disciplines, and are any interface conflicts currently identified that may impact subsequent DMP stages? | PgMC | C
21 | Baseline | Step I | MCA servicing strategy | MCA Servicing Strategy – General | MP | Have the servicing demand assumptions and capacity requirements been validated against the latest development program and phasing strategy? | PgMC | C
22 | Baseline | Step I | MCA servicing strategy | MCA Servicing Strategy – General | MP | Have all stakeholder and authority confirmations related to MCA servicing requirements been obtained, and are any remaining items required to be formally closed prior to progression into the next DMP stage? | PgMC | C
23 | Baseline | Step I | MCA servicing strategy | MCA Servicing Strategy – General | MP | Please clarify key operational assumptions adopted for the proposed servicing strategy and identify any potential impacts on circulation, accessibility, and adjacent developments. | PgMC | C
24 | Baseline | Step I | MCA servicing strategy | MCA Servicing Strategy – General | MP | Has a preferred loading bay and servicing strategy been identified? If so, please provide the rationale for selection over alternative scenarios and identify impacts on traffic operations, servicing routes, and underground interfaces. | PgMC | C
25 | Baseline | Step I | MCA servicing strategy | MCA Servicing Strategy – General | MP | Has the operational strategy for back-of-house servicing and loading movements been validated against peak pedestrian and crowd movement scenarios to avoid operational conflicts? | PgMC | C
26 | Baseline | Step I | MCA servicing strategy | MCA Servicing Strategy – General | MP | Have servicing routes and loading bay operations been coordinated with emergency access and public realm strategies to avoid interface conflicts? | PgMC | C
27 | Baseline | Step I | MCA servicing strategy | MCA Servicing Strategy – General | MP | Please demonstrate that the proposed operational approach does not create conflicts between BOH functions and primary pedestrian movement corridors. | PgMC | C
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## BLANK
REVIEW AND COMMENT SHEET |  |  | WorkStream: | INFRASTRUCTURE
| Submission: | Baseline | Revision: | V01 | Doc Ref.: |  | Prepared by: |  |  |  | Date:
COMMENT IDENTIFICATION | [5 empty] | ROUND 1 – CLIENT / RUA |  |  |  | ROUND 1 – DESIGNER RESPONSE |  |  | ROUND 2 – CLIENT / RUA |  |  |  | ROUND 2 – DESIGNER RESPONSE |  |  | ROUND 3 – CLIENT / RUA |  |  |  | ROUND 3 – DESIGNER RESPONSE |  |  | FINAL (CLIENT ONLY)
No. | Submission | Milestone | Topic | Doc / Drawing Ref. | Discipline | R1 – RUA Comment | R1 – Comment By | R1 – Status (CLIENT ONLY) | CRITICAL | R1 – Designer Response | R1 – Response By | R1 – Response Date | R2 – RUA Comment | R2 – Comment By | R2 – Status (CLIENT ONLY) | CRITICAL | R2 – Designer Response | R2 – Response By | R2 – Response Date | R3 – RUA Comment | R3 – Comment By | R3 – Status (CLIENT ONLY) | CRITICAL | R3 – Designer Response | R3 – Response By | R3 – Response Date | Final Status (CLIENT ONLY) | CRITICAL | Remarks / Notes
1 | Baseline | Step I
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200